## Read me
PeopleOS customer implementation checklist
For: the customer implementation team and the Markedge implementation lead. One row per stage; fill Status, Date, Owner sign-off and Notes as you go.
Mode says how each stage is done today: Configuration in PeopleOS, Operator action in PeopleOS (Markedge), Automated by PeopleOS, Manual (outside PeopleOS), or Blocked (a known defect or a release gate).
Navigation paths are the real menu paths of the application (verified in the training environment on 21 October 2026, commit 72c96a73). Deck 04 shows each screen.
Release context: the PeopleOS release gate is NO-GO (10 of 14 gates blocked, re-verified 13 October 2026). Stages 10, 17 and 26 are blocked until a defect fix, statutory verification and the release decision respectively.

## Implementation stages
# | Stage | Responsible | Mode | Required inputs | Navigation (real menu path) | What to enter or configure | Expected outcome | How to verify | Evidence to retain | Common errors / known limits | Dependencies and blockers | Acceptance criteria | Status | Date | Owner sign-off | Notes
1 | Discovery and implementation plan | Markedge implementation lead with the customer HR lead | Manual (outside PeopleOS) | Org charts, entity list, policies (leave, attendance, payroll), headcount, integrations, go-live date | Outside PeopleOS (workshops, plan) | Agree scope (modules, countries, payroll in or out), roles, data owners, timeline | Signed scope and plan | Customer sign-off on the scope document | Scope and plan, signed | Promising payroll go-live while statutory rules are unverified | Release gate NO-GO: general availability not yet declared | Scope lists every module and whether payroll statutory processing is in scope
2 | Tenant provisioning | Markedge platform operator (MFA required) | Operator action in PeopleOS | Customer name, slug, country, time zone, currency, first administrator name and e-mail, reason | Platform home › Manage tenants › New tenant | Tier, data region (metadata), name, slug (suggested from the name; check it before saving), status, locale, currency, first administrator; audit reason | Tenant created with default organisation set-up; invitation e-mailed to the first administrator | Tenant row is Active; invitation sent (or resend from the Tenants list) | Tenants list screenshot; audit entry | Mail not configured: "Tenant created, but the invitation e-mail was not sent" | Production mail transport (gate 8) | Tenant exists, first administrator invited
3 | First administrator activation | Customer administrator | Configuration in PeopleOS | Invitation e-mail (link valid 72 hours, single use) | Invitation link › Accept your invitation › Activate my account | Choose a password; sign in | Administrator signed in to an empty tenant | Users list shows the administrator Active | Users list | Expired or used link; one e-mail address can belong to only one organisation | Stage 2 | Administrator can sign in
4 | Company set-up | Customer administrator | Configuration in PeopleOS | Company names, legal names, codes, effective dates | Organisation › Organisation › Companies | Company name, legal name, code, effective from | Company listed; PeopleOS also creates a primary legal entity and a principal establishment for it automatically | Companies, Legal Entities and Establishments lists | Companies list | Duplicate codes (unique within the tenant) | Stage 3 | Every employing company exists
5 | Legal entities | Customer administrator with finance | Configuration in PeopleOS | Legal employer details (PAN, TAN, CIN where applicable) | Organisation › All in Organisation › Legal Entities | Review and complete the primary legal entity created with the company; add more only for additional legal employers | Legal entities recorded | List shows each entity and its status | Legal entities list | Treating a location as a legal identity | Stage 4 | Each legal employer recorded
6 | Establishments and locations | Customer administrator | Configuration in PeopleOS | Registered places of work (PF/ESI codes, PT/LWF state); physical sites | Organisation › All in Organisation › Establishments; Organisation › Locations | Complete the principal establishment created with the company; add further registered places of work; locations with state | Establishments and locations listed | Locations appear in hire and position forms | Lists | Locations cannot be linked to an establishment on screen (F10); the state list holds 13 Indian states | Stage 5 | Every site where people work exists
7 | Organisation structure | Customer HR lead | Configuration in PeopleOS | Business units, divisions, departments, teams, cost and profit centres | Organisation › Departments / Teams; Organisation Designer; Org map | Create units under their parents | Organisation tree | Org map shows the tree | Org map screenshot | Mixing financial and reporting units | Stage 4 | Tree matches the agreed org chart
8 | Job architecture and positions | Customer HR lead | Configuration in PeopleOS | Designations, levels, grades, job families, employment types, categories, work modes; positions if used | Admin › Setup › All in Setup › Designations, Grades, Levels…; Organisation › Workforce › Positions | Reference lists; draft positions | Lists available in the hire wizard | Hire wizard drop-downs show the values | Lists | FTE fields refuse whole numbers such as 1 (F8): leave blank | Stage 7 | Every designation and grade in the data file exists
9 | Employee data preparation | Customer HR data owner | Manual (outside PeopleOS) | Current employee master | Outside PeopleOS (spreadsheet) | Clean names, e-mails, joining dates, managers, units; one row per person | Validated data file | Row counts reconcile with payroll headcount | Data file and reconciliation sheet | Personal identifiers sent by e-mail; duplicate people | Stages 4–8 | Data owner signs off the file
10 | Data load | Customer administrator with Markedge | Blocked (defect or gate) | Validated data file | People › Lifecycle › All in Lifecycle › Employee imports (Upload → Inspect → Map columns → Validate → Approve → Run) | Upload works; Map columns fails with "Undefined variable $svc" (F25) | Import cannot progress past "inspected" from the screen | Import status | Import record and error message | F25 defect. Workarounds: the Hire employee wizard per person (verified in this training), or POST /api/v1/employees with an API key (in the OpenAPI specification; not exercised in this training) | Engineering fix for F25 | Every row loaded once; counts reconcile
11 | Person matching and duplicates | Customer HR | Automated by PeopleOS | Person details at hire | People › Lifecycle › Employees › Hire employee (Person step) | Nothing: the wizard checks for an existing person | Definite duplicates refused; possible duplicates warned | Directory shows one record per person | Wizard warning screenshot | Ignoring a "possible duplicate" warning | Stage 10 | No duplicate person records
12 | Roles, users and access scope | Customer administrator | Configuration in PeopleOS | Who does what; which companies or units each HR user covers | Admin › Setup › Users (New user = invitation); Admin › Setup › Roles | Invite users with roles; set organisation scope for HR users | Users invited and active | Sign in as each role (test accounts) and check the menus | Users list; role matrix | Leaving HR users without scope gives them the whole tenant (Home warns); Tenant HR Admin cannot edit role permissions (F5) | Stage 3 | Each user sees only what the role matrix says
13 | Reporting relationships | Customer HR | Configuration in PeopleOS | Manager of each employee | Hire employee (Manager step) or Employee 360 › Action › Change manager | Primary line manager; functional, dotted, mentor etc. where used. Only employed people can be chosen: hire and Mark as joined the managers first | Org chart and approvals route to managers | Org map; a test leave request reaches the manager | Org map | Missing managers: approvals have nobody to route to | Stage 10 | Every active employee has a primary manager (except the top)
14 | Attendance and shifts | Customer HR (attendance) | Configuration in PeopleOS | Shifts, weekly patterns, holiday list, devices | People › Time & leave › All in Time & leave › Shifts, Work Schedules, Holiday Calendars, Devices | Shifts, schedules with rules, holiday calendars with rules, devices | Attendance processes per schedule | Process a test day; check records | Attendance records | Holiday type and half-day are ignored: every holiday is a full day (F39); late-mark actions not applied (F40) | Stage 7 | A sample week processes as expected
15 | Leave policies | Customer HR | Configuration in PeopleOS | Leave types and entitlements | People › Time & leave › All in Time & leave › Leave types; Workflows › Policies (Leave policy) | Types; policy versions (accrual, probation, notice, carry forward, encashment) | Balances accrue | Balances for sample employees | Balances list | Hourly leave and sandwich rules not available (F43); encashment has no amount or payroll posting (F41) | Stage 10 | Sample balances match the customer's policy
16 | Payroll components and structures | Customer payroll lead | Configuration in PeopleOS | Salary components, structures, CTC per employee | People › Pay › All in Pay › Salary components, Salary structures | Components with formulas; structure versions (approval) | Runs can be calculated | Calculate a test run; Payroll Auditor | Run breakdown | Statutory components are reserved; monthly frequency only | Stage 10 | Test run gross and net match a reference calculation
17 | Statutory configuration and verification | Customer payroll (registrations); Markedge (rule verification) | Blocked (defect or gate) | Registrations (PF, ESI, PT, LWF, TAN), establishment profiles; official rule evidence | People › Pay › All in Pay › Statutory registrations, Statutory profiles; Compliance control room; Rule verification | Customer records registrations against an establishment first, then establishment statutory profiles; two platform administrators verify each rule with evidence | Finalisation allowed only when rules are verified | Compliance control room shows no unverified rule | Verification register | 0 of 24 rules verified today; gratuity not calculated; no rules for USA, UK, EU; a profile recorded before its registration has no registration linked | Owner decisions O-5, O-12, O-18 | All rules in scope verified, or payroll excluded from scope in writing
18 | Workflows and approvals | Customer HR with Markedge | Configuration in PeopleOS | Approval chains per request type | Workflows › Workflows (builder, versions); Workflows › Policies | Publish workflow versions; leave/attendance approvals go to the line manager by default | Requests route correctly | Run each request type once in UAT | Workflow runs | "Generate document" step skipped (F33) | Stage 13 | Every request type reaches the right approver
19 | Notifications and communication | Customer HR | Configuration in PeopleOS | Which events notify whom | Communication › Notification rules, Notification templates, Delivery log | Edit starter rules and templates | E-mail and in-app notices sent | Delivery log shows sent items | Delivery log | No role can create or delete rules (F18); SMS, WhatsApp, push send nothing (F19) | Production mail transport | Agreed notifications appear in the delivery log
20 | Security policy and sign-in | Customer administrator | Configuration in PeopleOS | MFA decision, password and session rules, SSO (OIDC) | Admin › Platform › Security policy; Single sign-on | Require MFA (recommended); idle timeout; OIDC connection | Policy enforced at sign-in | Sign in as a test user | Security policy screenshot | Password expiry is stored but not enforced (F2); SAML not supported | Stage 12 | MFA required for administrators at least
21 | Employee and manager readiness | Customer HR with Markedge trainer | Manual (outside PeopleOS) | Decks 1 and 2 | Training sessions; Home of each persona | Invite pilot users; run the exercises | Pilot users trained | Exercise completion | Attendance list | Training before data is final | Stages 10–15 | Pilot group completes the exercises
22 | Data validation and reconciliation | Customer data owner | Configuration in PeopleOS | Source counts by company, unit, status | Insights › Reports (starter reports, Export CSV); People analytics; Employees register filters | Run headcount reports and compare | Counts reconcile | Signed reconciliation | Export and reconciliation sheet | Report builder filter/group lists empty (F44): use starter reports and filters | Stage 10 | Zero unexplained differences
23 | User acceptance testing | Customer UAT lead | Manual (outside PeopleOS) | UAT test cases (supporting workbook) | Each module as the tester's role | Execute cases, record actual results and evidence | UAT log | Pass rate and open defects | UAT workbook with screenshots | Testing with real personal data in a shared environment | Stages 2–22 | All critical cases pass; no open critical defect
24 | Defect logging and resolution | Markedge support and engineering | Manual (outside PeopleOS) | Failed test cases | Outside PeopleOS (defect tracker) | Log, triage, fix, retest | Defects closed or accepted | Retest evidence | Defect log | Closing without retest | Stage 23 | Known defects (F25, F38, F44, F17…) fixed or accepted in writing
25 | Security and access validation | Customer administrator with Markedge | Configuration in PeopleOS | Role matrix | Admin › Setup › Roles, Users; Insights › Audit › Change history | Sign in as each role; try restricted pages | Access matches the matrix | Restricted pages show "not available" | Access test log | Testing only as a super administrator | Stage 12 | No role sees more than agreed
26 | Go-live readiness and approval | Customer sponsor and Markedge | Blocked (defect or gate) | UAT sign-off, reconciliation, open defects, release gate | Platform readiness (operator); outside PeopleOS (approval) | Go/no-go meeting | Written go-live approval | Release gate GO and customer sign-off | Signed approval | Going live while the release gate is NO-GO | Release gate (10 of 14 gates blocked today) | GO decision recorded by both parties
27 | Post-go-live monitoring and support handover | Markedge support and platform operations | Operator action in PeopleOS | Hypercare plan, contacts | Platform › Operations (queues, failed jobs); Platform audit trail; Delivery log | Daily checks during hypercare; hand over to support | Stable operation | No failed jobs; tickets within SLA | Hypercare log, handover checklist | No scheduler or queue worker running | Hosting and on-call (gate 8) | Handover checklist signed
28 | Customer training and ongoing governance | Customer HR with Markedge | Manual (outside PeopleOS) | Training library; governance calendar | Change Centre; Change history; Reports | Quarterly access review; policy version reviews; release notes | Governance rhythm | Review minutes; Change history › Verify integrity reports "Chain intact" | Access review records | Unreviewed tenant-wide HR access | Stage 27 | First quarterly review held