## Read me
PeopleOS go-live and support handover checklist
For: the customer sponsor, the customer HR lead and Markedge support. Complete every row before support takes over from the implementation team.
Rows marked Operations depend on a hosted environment, monitoring and on-call, which are blocked release gates today (gate 7 and 8).

## Handover
Area | Item | Responsible | Evidence | Status | Date | Signed by | Notes
Access | Customer administrators active; Markedge implementation accounts removed or suspended | Customer admin + Markedge lead | Users list export
Access | Every role tested against the agreed role matrix (allowed and restricted pages) | Customer admin | Access test log
Access | MFA required for administrators (Security policy); operator MFA enrolled in production | Customer admin; Markedge operators | Security policy screenshot; readiness
Access | HR users have organisation scope where they should not see the whole tenant | Customer admin | Users › scope screenshot
Configuration | Organisation, job architecture and locations match the signed design | Customer HR lead | Org map; lists
Configuration | Leave types and policy versions published; sample balances reconciled | Customer HR | Balances export
Configuration | Shifts, schedules and holiday calendars assigned; a sample week processed | Customer HR (attendance) | Attendance records
Configuration | Workflows and notification rules reviewed; delivery log shows sent items | Customer HR | Delivery log
Data | Headcount reconciled by company, unit and status (zero unexplained differences) | Customer data owner | Reconciliation sheet
Data | No duplicate people; managers set for all active employees | Customer HR | Directory and register filters
Payroll and statutory | Statutory registrations recorded; statutory rule verification status agreed (0 of 24 verified today) | Customer payroll; Markedge | Compliance control room
Payroll and statutory | Parallel or reference payroll compared before the first live run (only when finalisation is allowed) | Customer payroll | Comparison sheet
Operations | Queue worker and scheduler running; no failed jobs (Platform › Operations) | Markedge platform operations | Operations screenshot
Operations | Backup schedule, restore test and recovery objectives agreed and evidenced | Markedge infrastructure | Restore test record
Operations | Monitoring and on-call contacts confirmed | Markedge | On-call rota
Support | Support channel, hours and escalation route communicated to the customer | Markedge support | Support handbook
Support | Known defects and workarounds shared (F25 import, F38 apply on behalf, F44 report builder, F17 feedback) | Markedge support | Known-issues list
Documentation | Training decks delivered; pilot users trained; exercise completion recorded | Markedge trainer | Attendance list
Governance | Quarterly access review and policy review dates agreed | Customer HR lead | Calendar invite
Sign-off | Go-live approval signed by the customer sponsor and Markedge, with the release gate decision recorded | Customer sponsor; Markedge | Signed approval