## Read me
PeopleOS UAT test cases
For: the customer UAT lead and testers. Execute each case in the customer's UAT tenant as the stated role, then fill Actual result, Evidence screenshot, Pass/Fail, Defect reference and Sign-off.
The "Reference run" columns record what Markedge observed when the same steps were executed in the training environment on 21 October 2026 (disposable database, fictional people). They are not the customer's result: Pass/Fail stays blank until the customer executes the case.
A reference outcome of "Not executed" means the case could not be run in the training environment; the reason is given.

## Test cases
Test ID | Module | Role | Preconditions | Steps | Expected result | Reference run outcome (training env) | Reference observation | Reference screenshot(s) | Actual result | Evidence screenshot | Pass/Fail | Defect reference | Executed by / date | Sign-off
UAT-LV-01 | Leave | Employee | Employee linked to a user; leave balances accrued; a line manager set | 1. Home › Request leave 2. Choose Casual leave; pick two working days; enter a reason 3. Check the Before → After preview 4. Submit request 5. Open People › Time & leave › Leave requests | Preview shows working days and the balance after; "Leave requested: N day(s)"; request listed as pending with Cancel available | Executed: matched expected | 14–15 Dec 2026 = 2 working days; Casual leave 5 → 3; "Leave requested: 2.0 day(s)"; listed as pending | employee/10-leave-04-form-completed employee/10-leave-05-submitted employee/10-leave-06-status-pending
UAT-LV-02 | Leave | Employee | Employee on probation; leave policy disallows Earned leave during probation | 1. Home › Request leave 2. Choose Earned leave; pick dates; enter a reason 3. Submit request | Request refused with the policy reason; nothing is created | Executed: matched expected | "Cannot apply. Earned leave is not available during probation." (the type list still offers Earned leave with its balance) | employee/10-leave-03-policy-refusal
UAT-LV-03 | Leave | Employee | As UAT-LV-01 | 1. Home › Request leave 2. Submit without choosing a leave type | Submission stopped at the first empty required field | Executed: matched expected | Browser prompt "Please select an item in the list." on Leave type | employee/10-leave-02-validation
UAT-LV-04 | Leave | Manager | A pending leave request from a direct report | 1. My work › Approvals 2. Select the request; read reason, overlap and balance before → after 3. Approve; add a note; Confirm: Approve | "Leave approved"; item leaves the queue; employee sees Approved and Reviewed by the manager; balance Used increases | Executed: matched expected | "Leave approved"; queue 7 → 6; employee list shows approved / Reviewed by Amit Verma; Casual leave Used 2.0, ledger usage −2.00 | manager/10-leave-08-decision-card manager/10-leave-09-approve-confirm manager/10-leave-10-approved employee/10-leave-13-status-approved employee/10-leave-14-balances employee/10-leave-15-ledger
UAT-LV-05 | Leave | Manager | A pending leave request from a direct report | 1. My work › Approvals 2. Select the request; Reject 3. Confirm: Reject with no reason 4. Enter a reason; Confirm: Reject | Rejection without a reason is stopped; with a reason it is recorded | Executed: matched expected | "Please fill out this field." then "Leave rejected" | manager/10-leave-11-reject-reason-required manager/10-leave-12-rejected
UAT-AT-01 | Attendance | Employee | Web check-in allowed; employee has a work schedule | 1. Home › Your day › Check in | "Checked in"; Your day shows the time and offers Check out | Executed: matched expected | "Checked in"; Check out offered | employee/20-att-01-your-day-check-in employee/20-att-02-checked-in
UAT-AT-02 | Attendance | Employee → Manager | A past working day with a missing punch | 1. Employee: Home › Start something › Fix my attendance; date, Missed punch, actual in/out, reason; Submit 2. Manager: My work › Approvals; select the correction; Approve; Confirm 3. Employee: People › Time & leave › Attendance records | Correction pending → approved; day reprocessed with the corrected times | Executed: matched expected | "Correction sent to your manager"; "Approved and attendance reprocessed"; 20 Oct Present 09:05–18:10 (flagged worked on holiday: Dussehra in the demo calendar) | employee/20-att-03-fix-my-attendance employee/20-att-05-regularisation-pending manager/20-att-06-correction-card manager/20-att-07-correction-approved employee/20-att-16-my-attendance
UAT-AT-03 | Attendance | Tenant HR Admin | attendance.manage permission | 1. People › Time & leave › Attendance records › Manual punch: employee, time, direction, note; Submit 2. Process day: choose the date; Submit 3. Check Exception centre and Punches | Punch recorded with source manual; day processed for all employees; exceptions listed | Executed: matched expected | "Punch recorded and day reprocessed"; "21 employee(s) processed for 2026-10-20" | hr-admin/20-att-11-manual-punch hr-admin/20-att-13-day-processed hr-admin/20-att-14-exception-centre hr-admin/20-att-15-punches
UAT-PR-01 | Provisioning | Platform operator | Operator account with MFA enrolled | 1. Platform › Tenants › New tenant 2. Enter name, locale defaults, first administrator, reason 3. Create tenant 4. Submit the same tenant again | Tenant created and first administrator invited; duplicate slug and e-mail refused | Executed: matched expected | Northwind Retail created; invitation e-mailed; second submit: "The slug has already been taken." / "The email has already been taken." | client-onboarding/90-onb-03-new-tenant-form client-onboarding/90-onb-04-duplicate-tenant-refused client-onboarding/90-onb-05-tenants-with-northwind
UAT-PR-02 | Provisioning | Customer administrator | Invitation e-mail received | 1. Open the invitation link 2. Enter a 6-character password; Activate 3. Enter a valid password; Activate 4. Open the same link again | Short password refused; activation succeeds; the link cannot be reused | Executed: matched expected | "The password field must be at least 8 characters."; "Your account is ready…"; "This invitation link is invalid or has expired…" | client-onboarding/90-onb-09-password-rules client-onboarding/90-onb-10-account-ready-sign-in client-onboarding/90-onb-11-invitation-used
UAT-ORG-01 | Organisation | Customer administrator | Empty tenant | 1. Create company, legal entity, establishment, location 2. Create business unit, departments, team 3. Place units in the Organisation Designer 4. Open the Org map | Structure visible in the designer tree, chart and org map | Executed: matched expected | Company creation also created a primary legal entity and principal establishment; tree Company → BU → departments → team | client-onboarding/90-onb-17-company-saved client-onboarding/90-onb-31-designer-tree client-onboarding/90-onb-32-designer-chart
UAT-HR-01 | People | Tenant HR Admin | Organisation and designations exist; an existing person to test duplicates | 1. People › Lifecycle › Employees › Hire employee 2. Enter an existing person's personal e-mail; Next 3. Enter a new person; complete Employment, Position, Manager; Create employee | Duplicate refused; new Employee 360 created with onboarding started | Executed: matched expected | "This person already exists: Priya Nair (EMP00004)…"; Tanvi Joshi EMP00023 created, Probation, onboarding started | hr-admin/50-hire-01-duplicate-refused hr-admin/50-hire-07-created-record
UAT-HR-02 | People | Tenant HR Admin | Employee and a second employed manager exist | 1. Employee 360 › Action › Change manager 2. Context: line manager; Change: new manager and date; Review: reason 3. Confirm reporting change | Reporting line changed from the date; previous line kept in history | Executed: matched expected | Amit Verma → Ravi Kumar; header "Reports to Ravi Kumar" | hr-admin/50-chg-07-manager-review hr-admin/50-chg-08-manager-done
UAT-HR-03 | Documents | Tenant HR Admin + HR Manager | Two HR users with document permissions | 1. HR user A uploads a document to an employee 2. HR user A tries to verify it 3. HR user B verifies it | A cannot verify own upload; B verifies; status Verified with verifier | Executed: known defect | Rule enforced, but shown as a server error ("The person who uploaded a document cannot verify it."); B verified successfully | hr-admin/50-doc-02-uploaded-pending security-compliance/50-doc-03-uploader-cannot-verify hr-admin/50-doc-05-verified |  |  |  | New (21 Oct 2026): refusal surfaces as HTTP 500
UAT-HR-04 | Onboarding | Tenant HR Admin | A new hire with an onboarding plan | 1. Employee 360 › Records › Employment › Onboarding 2. Done on an open task; confirm | Task done with who and when; progress increases | Executed: matched expected | Task status done; plan progress moved up | hr-admin/50-onb-04-task-done-confirm hr-admin/50-onb-05-task-completed
UAT-LV-06 | Leave | Tenant HR Admin | Employee with a leave balance | 1. Leave requests › Apply on behalf 2. Employee 360 › Records › Time › Apply for leave; submit | HR can apply leave for an employee | Executed: known defect | Apply on behalf: server error (F38). The Employee 360 route works and the request goes to the approver | support/55-lv-err-01-apply-on-behalf hr-admin/55-lv-11-apply-form hr-admin/55-lv-12-applied |  |  |  | F38
UAT-LV-07 | Leave | Tenant HR Admin | A balance row exists | 1. People › Time & leave › Balances › Adjust: days and note 2. Open Transactions | Adjusted and Available updated; ledger entry with the note | Executed: matched expected | Casual leave adjusted 1.0; ledger entry recorded | hr-admin/55-lv-03-adjusted hr-admin/55-lv-04-ledger
UAT-IMP-01 | Imports | Tenant HR Admin | A 2–3 row CSV of fictional people | 1. Employee imports › Upload CSV 2. Inspect file 3. Map columns; Submit | Mapping saved; Validate available | Executed: known defect | "Failed — Undefined variable $svc"; import stays inspected (reproduced in two tenants) | client-onboarding/90-onb-92a-import-inspected client-onboarding/90-onb-93-import-map-fails |  |  |  | F25
UAT-PAY-01 | Payroll | Payroll Admin | Salaries assigned; payroll run for the month | 1. Payroll runs › open the run 2. Recalculate 3. Validate | Run calculated; validation passes when rules are verified | Executed in part | "Calculated for 19 employee(s); 19 with exceptions"; Validate refused: "19 employee(s) have blocking exceptions" (statutory rules unverified) | hr-admin/60-pay-08-recalculated hr-admin/60-pay-09-validate-blocked |  |  |  | Release gate 5 (by design)
UAT-PAY-02 | Payroll | Payroll Admin, Tenant HR Admin | A validated run (not reachable today) | 1. Approve (a different person from the creator) 2. Finalize & generate payslips 3. Bank file; Mark as paid | Payslips generated; employees see them | Not executed | Not reachable: validation blocked by unverified statutory rules |  |  |  |  | Release gate 5
UAT-CMP-01 | Compensation | HR Manager → Tenant HR Admin → Tenant Super Admin → Payroll Admin | Four different people with the four duties | 1. Propose and submit for review 2. Mark reviewed 3. Reviewer opens actions (expect no Approve) 4. Third person approves 5. Fourth person executes | Each step by a different person; status Scheduled | Executed: matched expected | Amit Verma 24,00,000 → 26,40,000; reviewer had no Approve; executed → Scheduled | hr-admin/62-comp-02-propose-form security-compliance/62-comp-07-reviewer-cannot-approve hr-admin/62-comp-10-executed
UAT-ACC-01 | Access | Tenant administrator | Test users per role | 1. Invite a user with a role and company scope 2. Sign in as that user 3. Open a page outside the role | Narrower menu; restricted page shows "not available" | Executed: matched expected | Rohit Menon (HR Executive) scoped to Northwind: Roles page refused | client-onboarding/90-onb-56-new-user client-onboarding/90-onb-59-hr-executive-home client-onboarding/90-onb-60-hr-executive-roles-denied
UAT-AUD-01 | Audit | Tenant administrator | Configuration changes made | 1. Insights › Audit › Change history 2. Verify integrity | Every change listed; chain intact | Executed: matched expected | "Chain intact: 287 events verified" (Northwind) | client-onboarding/90-onb-89-audit-trail client-onboarding/90-onb-90-audit-verified
UAT-RPT-01 | Reports | Tenant HR Admin | Starter reports present | 1. Insights › Reports › Headcount by department › Run 2. Export CSV 3. Change history: find the Export event | Grouped results; CSV downloaded; export audited | Executed: matched expected | Engineering 12, Design 4, — 3, Consulting 2, Finance 1; CSV downloaded; Export event recorded | analytics/80-ins-06-report-result analytics/80-ins-10-change-history
UAT-RPT-02 | Reports | Tenant HR Admin | Report permissions | 1. Reports › New report 2. Choose dataset Employees 3. Open Group by and Sort by | Dataset fields offered for grouping, filters and sorting | Executed: known defect | Only "No grouping" and "Dataset order ¦ Count" offered | analytics/80-ins-08-report-builder-f44 |  |  |  | F44
UAT-PLT-01 | Platform | Platform operator | A non-production tenant | 1. Tenants › Suspend with reason 2. Tenant administrator signs in 3. Reactivate | Sign-in refused while suspended; works after reactivation; both audited | Executed: matched expected | Generic credentials message while suspended; reactivated; platform audit shows both with reasons | platform-admin/95-pl-07-suspended platform-admin/95-pl-08-suspended-sign-in platform-admin/95-pl-09-reactivated platform-admin/95-pl-37-platform-audit-after
UAT-PLT-02 | Platform | Platform operator (two) | Two operator accounts | 1. Offboarding › tenant › Place legal hold 2. Request release 3. A second operator approves the release | Hold active; release only after a second operator approves | Executed in part | Hold LH-2026-01 placed; release requested and pending (only one operator exists) | platform-admin/95-pl-27-legal-hold-active platform-admin/95-pl-34-release-pending
UAT-SUP-01 | Sign-in | Any user | Mail delivered to the user | 1. Forgot password? › e-mail › Send email 2. Open the link; set a new password 3. Open the same link again | Neutral answer; password changed; link single-use | Executed: matched expected | Neutral message; "Your password has been changed…"; used link refused | support/99-sup-03-reset-requested support/99-sup-05-reset-done support/99-sup-06-reset-link-used
UAT-ESS-01 | Self-service | Employee | HR request categories configured | 1. Services › My HR › Ask HR: category, subject, description, priority; Submit 2. Open You › My requests | Numbered request with SLA; listed as Submitted | Executed: matched expected | TKT-2026-00002 raised; My requests shows Submitted with SLA 2 days | employee/30-self-36-ask-hr-form employee/30-self-37-ask-hr-submitted employee/30-self-38-my-requests
UAT-ESS-02 | Self-service | Employee → HR Manager | An open employee request | 1. HR: Services › HR queue › request › Take it, Reply, Resolve 2. Employee: My requests (clear the status filter) › request | Employee sees Resolved with HR's answer | Executed: matched expected | TKT-2026-00003 resolved; visible under Resolved after clearing the default status filter | hr-admin/52-tkt-05-resolved employee/52-tkt-06-my-requests employee/52-tkt-07-request-answer
UAT-ESS-03 | Self-service | Employee | Feedback categories configured | 1. My HR › Give feedback: mode, category, text; Submit | Feedback sent to the HR inbox with a confirmation | Executed: known defect | "Not allowed" with a raw SQL error (feedback stored; HR not notified) | employee/30-self-44-give-feedback-form employee/30-self-45-give-feedback-error |  |  |  | F17
UAT-ESS-04 | Pay | Employee | Tax declaration window open | 1. Tax declarations › New: financial year, regime, amounts; Create 2. Look for a Submit action | Declaration submitted to payroll | Executed: known defect | Saved as Draft; no employee Submit action | employee/30-self-21-tax-declaration-form employee/30-self-22-tax-declaration-saved |  |  |  | F13
UAT-GRW-01 | Performance | Employee | A goal with a key result | 1. People › Growth › Goals › Check in: key result, current value, confidence, note | Progress recalculated | Executed: matched expected | "Progress updated": 55% → 70% (value 68 of target 80, start 40) | employee/30-self-25-goal-check-in employee/30-self-26-goal-updated
UAT-GRW-02 | Performance | Employee → Manager | Cycle in Self review stage | 1. Employee: Appraisal › Self review › Submit 2. Manager: Appraisal › Manager review › Submit (before HR opens the stage) | Self review submitted; manager review accepted once its stage opens | Executed in part | Self review submitted (4.00); manager review refused: "The Manager review stage has not opened yet." | employee/30-self-29-self-review-submitted manager/40-team-25-manager-review-stage-closed |  |  |  | F21 (stages do not advance by date)
UAT-GRW-03 | Learning | Employee | An assigned course | 1. You › My learning › enrolment › Start | Status In progress | Executed: matched expected | "Started"; In progress | employee/30-self-33-enrolment employee/30-self-34-enrolment-started
UAT-LTR-01 | Letters | HR Manager + Tenant HR Admin | A letter template that needs approval | 1. HR user A: Letters › Generate letter 2. HR user A: Approve (expect refusal) 3. HR user B: Approve, then Issue 4. Employee: My letters | Requester cannot approve; issued letter visible to the employee | Executed: matched expected | "The person who requested a letter cannot approve it."; issued; visible in My letters | security-compliance/52-let-04-requester-cannot-approve hr-admin/52-let-06-issued employee/52-let-07-my-letters
UAT-AST-01 | Assets | Tenant HR Admin | An asset in stock | 1. Asset register › asset › Assign: employee, condition, note 2. Employee: My assets | Status Assigned; custody history; employee sees the asset | Executed: matched expected | LT-0004 assigned to Tanvi Joshi; custody history from today | hr-admin/52-ast-03-assigned employee/52-ast-04-my-assets
UAT-EXT-01 | Exit | Employee → Manager → HR | Employee with an asset in custody | 1. Employee: My exit › Resign 2. HR: Start clearance; manager clears own stage 3. HR: clear asset stage (expect refusal), take the asset back, clear 4. HR: exit interview; full & final: calculate, approve, mark paid 5. HR: Complete exit; Create alumni profile | Exit completed; alumni profile; employee Exited | Executed: matched expected | Asset stage refused until LT-0001 returned; F&F net 38,254.06 paid; exit completed; alumni created. Gratuity not calculated; same person calculated and approved F&F | hr-admin/70-exit-08a-asset-stage-blocked hr-admin/70-exit-11-ff-settlement hr-admin/70-exit-15-completed hr-admin/70-exit-18-employee-exited
UAT-EXT-02 | Alumni | Alumnus → HR | Exited employee with alumni portal enabled | 1. Alumnus signs in › Request a document or reference 2. HR: Alumni › person › Requests | Request reaches HR with identity verification | Executed: matched expected | ALR-2026-00001 requested; HR sees Verify identity / Approve & generate | employee/70-alumni-01-portal employee/70-alumni-03-requested hr-admin/70-alumni-04-hr-requests